## Annex I Update Action Plan2013
Area |  | Actions required from CAs | Status of action | Summary of progress/accomplishment | Deadline | Actions required from EBA staff in 2013 | Status of action | Summary of progress/accomplishment | Deadline for EBA staff action
EBA Coverage of Colleges | EEA cross border banking groups | Competent authorities, in their capacity as consolidating supervisors, to notify EBA i) on the cross border banking groups under their jurisdiction, ii) on the establishment of colleges for the banking groups meeting CRD criteria | Accomplished | Information has been provided accordingly. | By 15 January | To collect and maintain a database with all EEA cross border banking groups | Accomplished | The database was created and updated on an ongoing basis. | ongoing
|  | For all EEA cross border banking groups to provide information on whether they have been qualified as global SIFIs or “European SIFIs”, and totals assets on a consolidated level as well as in the home jurisdiction. | Accomplished |  |  | To collect and maintain a database with all EEA colleges established | Accomplished
|  | For the colleges that have been set up to notify reaching a joint decision in 2012 | Accomplished |  |  | To follow-up on the cases where joint decisions in 2012 have not been reached | Accomplished | EBA staff followed all cases and assisted NSAs.
|  | For colleges that have not been set up, competent authorities to communicate the reasons of non-establishment and intended follow-up actions | Accomplished | The colleges have been established, though in a few cases were not active during 2013. |  | To follow-up on the cases for which colleges have not been set-up yet | Accomplished | The colleges have been established, though in a few cases were not active during 2013.
| Closely monitored colleges | For closely monitored colleges to provide more detail information on colleges' composition and settings. | Accomplished |  |  | To collect and analyse the data submitted, applying also qualitative criteria in order to produce a proposed list of `closely monitored colleges` | Accomplished | Criteria have been set up. The list of closely monitored colleges has been updated. BoS has been informed. | By Feb BoS meeting (27-28/02)
[6 empty] | To update BOS on the information received for all EEA cross border banking groups and establishment of colleges | Accomplished
| Non-EEA cross border banking groups present in EEA | EEA competent authorities to communicate to the EBA the banking groups with a parent undertaking in a third country that have presence in their jurisdiction. | Accomplished | Information has been provided accordingly. | By 15 January | To collect and maintain a database with all non-EEA cross border banking groups with presence in EEA | Accomplished | Database of non-EEA cross border banking groups has been completed. | By Feb BoS meeting (27-28/02)
|  | For these entities, the CAs to i) notify the existence of a college; and ii) note their assessment with regards to whether the CRD requirements for the establishment of colleges are met, indicating sub-consolidating EEA supervisor. | Accomplished |  |  | To collect and maintain a database with all colleges established | Accomplished | Database on colleges of non-EEA cross border banking groups has been completed.
[6 empty] | To update BOS on the information received for all these cross border banking groups and establishment of colleges | Accomplished | BoS has been informed.
| Mapping template | Competent authorities, in their capacity as consolidating supervisors for the colleges that has been identified as “Closely Monitored Colleges” to submit to EBA the mapping template; | Accomplished |  | By 29 March | To collect and maintain a library of the mapping templates for the `closely monitored` colleges | Accomplished | Templates have been collected. Mapping charts have been developed offering transparent overiview on groups` sturctures. | ongoing
College Meetings |  | Competent authorities, in their capacity as consolidating supervisors for the colleges that have been identified as “Closely Monitored Colleges” to organise at least one physical meeting with the participants of the general colleges and notify EBA about these meetings as well as other forms of gatherings (e.g. telcos, emails): | Largely accomplished | For 3 colleges no physical college meetings were organised. | By end of November | To monitor college cooperation and meetings | Accomplished | Staff presence at all college meetings was ensured. Only meetings focused on specific or technical topics were not attended. | ongoing
Coordinated supervisory activities |  | Competent authorities, in their capacity as consolidating supervisors for the colleges that have been identified as “Closely Monitored Colleges” to discuss with host supervisors the areas of joint work, based on the activities/issues of the banking group and also on the results of the previous JRAD process | Partially accomplished | Many colleges approached the coordinated action plan as a compilation of the individual supervisory actions planned by college members. | By 29 March | To keep a library of the coordinated supervisory action plans for the `closely monitored` colleges | Accomplished | Supervisory action plans were collected and filed, though 3 action plans haven`t been received. | ongoing
|  | CAs to submit to EBA the coordinated action plan for 2013 | Largely accomplished | 3 action plans have not been received from CAs.
JRAD process |  | Competent authorities, in their capacity as consolidating supervisors for the colleges that have been identified as “Closely Monitored Colleges” to submit to EBA: |  |  |  | To support improvements on the JRAD process through short and long term policy work (e.g. Good Practices Document, draft ITS on capital JD) | Accomplished | Draft ITS on capital JD have been elaborated, template for JD document prepared. | ongoing
|  | Agreed timeline for the joint risk assessment and joint decision process (JRAD timeline) if not already indicated in the coordinated supervisory action plan | Largely accomplished | The information was not received from 3 CAs. | Within 3 months from the reach of the previous joint decision, but no later than 29 March 2013 | To provide guidance by promoting the use of the Q&A section on the member`s only website | Accomplished | Q&A section of the website was intensely used.
|  | Draft joint risk assessment report | Partially accomplished | Draft joint risk assessments have not been received from 8 CAs. | As per the agreed timeline | To promote the best practices observed in colleges | Accomplished | Feedback was provided to consoldiating supervisors after all college meetings. Feedbacks aimed to disseminate best practice. College workshop was organised by EBA in June 2013. The micro risk dashboard was provided for all colleges attended by EBA staff.
|  | Final risk assessment report | Partially accomplished | as per previous |  | To organise a college workshop in the course of 2013 | Accomplished
|  | Draft joint decision document | Partially accomplished | Draft joint decisions have not been received from 10 CAs. |  | To provide feedback following participation of college meetings | Accomplished
|  | Final joint decision document, or in the absence of JD, the unilateral decisions taken by all CAs | Partially accomplished |  | As per agreed timeline, but no later than 12 months from the reach of the previous joint decision | To promote the use of the EBA risk dashboard by providing tailor made presentations in college meetings and updates from the EBA risk analysis work | Accomplished
Crisis management |  | As per EBA recommendation subject to BoS approval (EBA/REC/2013/02 EBA Recommendation on development of recovery plans) | Partially accomplished | 14 colleges discussed the recovery plan within the framework of the college meetings. | As per EBA recommendation | As per EBA recommendation | Accomplished | Feedback has been provided to consolidating supervisors on recovery plans submitted to EBA. | ongoing
|  | Emergency plans |  | 81% plans received |  | To develop a Good Practices Document and/or Template on Emergency Plan | Largely accomplished | Template on Emergency plan has been elaborated. | To be determined
Secure information exchange |  | Competent authorities willing to use the EBA IT platform to express their interest to EBA | Accomplished | 3 NSAs expressed their intereset to use EBA IT Tool. | Ongoing | Promoting the use of the EBA IT platform | Accomplished | Training for 3 NSAs and continuous support from EBA. | ongoing
[6 empty] | Providing training on the use of the EBA IT platform to the competent authorities interested in adopting the platform | Accomplished
[6 empty] | Improving the technical support relevant for the use of the IT platform | Accomplished