## Annex II Action Plan 2014
Action Plan of Colleges for 2014
Topic |  | Actions required from competent authorities | Template | Deadline | Actions required from EBA staff | Deadline
Cross-border banking groups in EEA | EEA cross border banking groups | Competent authorities to notify EBA on the cross border banking groups under their jurisdiction | Annex III table I (a) | By 3 February | To collect and maintain a database with all EEA cross border banking groups | Ongoing
|  | Consolidating supervisors to notify EBA on the establishment of colleges for the banking groups meeting CRD requirements | Annex III table I (a) | By 3 February | To collect and maintain a database with all colleges established in EEA | Ongoing
|  | For colleges that have not been set up competent authorities to notify the reasons of non-establishment and intended follow-up actions | Annex III table I (a) | By 3 February | To follow up on cases for which colleges have not been set up yet | Ongoing
| Cross-border banking groups operating in EEA with parent in a third country | Competent authorities to notify EBA on the cross-border banking groups with parent in a third country operating in their jurisdiction | Annex III table I (b) | By 3 February | To collect and maintain a database with all cross-border banking groups operating in EEA with parent in a third country | Ongoing
|  | Consolidating supervisors to notify EBA on the establishment of colleges for cross-border banking groups operating in EEA with parent in a third country | Annex III table I (b) | By 3 February | To collect and maintain a database with all colleges for cross-border banking groups operating in EEA with parent in a third country | Ongoing
[5 empty] | To assess the options to organise sub-consolidated supervisory collaboration at the EEA level for cross-border banking groups operating in EEA with parent in a third country | By 15 February
| Closely monitored colleges |  |  |  | To propose a selection of colleges that will be closely monitored based on the application of quantitative and qualitative criteria | By 15 February
|  | Consolidating supervisors for closely monitored colleges to submit to EBA details on college composition, structure, and contact persons | Annex III table I (c) | By 28 March | To collect and maintain a database with all information on EEA closely monitored colleges | Ongoing
| Transition to SSM |  |  |  | To provide support to SSM for the smooth transition of supervisory tasks | Ongoing
[5 empty] | To provide support to SSM for the review of cooperation agreements in the re-establishment of colleges under the SSM | Ongoing
|  | Consolidating supervisors to notify EBA on the amendments in college composition, cooperation agreements, and contact details following the transition to SSM supervision |  | Ongoing | To collect and update information on amendments in college composition, cooperation agreements, and contact details following the transition to SSM supervision | Ongoing
Regular college activities | College Meetings | Consolidating supervisors for closely monitored colleges to organise at least one physical meeting with the participants of the general colleges and notify EBA about these meetings as well as other forms of gatherings (e.g. telcos) |  | By end of November | To monitor organisation of college meetings and arrange for participation in relevant meetings. To provide feedback on college meetings. | Ongoing
| Coordinated supervisory action plan | Consolidating supervisors for closely monitored colleges to prepare within the college the coordinated action plan for 2013, based on the results of the previous JRAD process and to submit the plan to the EBA |  | By 28 March | To collect and maintain a database with all college supervisory action plans, and follow up on the implementation of the action plans | Ongoing
Regular college activities | JRAD process | New ITS on Capital and Liquidity Joint Decision:
[5 empty] | To provide ITS training targeted especially to all consolidating supervisors | To be determined
[5 empty] | To provide detailed presentations on ITS guidelines and templates in all colleges attended by EBA staff | Ongoing
Joint Risk Assessment and Joint Decision on capital:
|  | Consolidating supervisors for closely monitored colleges to submit to EBA the timeline for reaching joint decision on capital adequacy (as set out in the ITS, and respecting the one year cycle) prepared and agreed by the college. It is important to note that the legal requirement on fulfilling the joint decision within 12 months from the last joint decision should be respected. |  | Within 3 months after reaching the previous joint decision, but no later than 28 March 2014 | To monitor roll out of agreed timeline for reaching joint capital decision | Ongoing
|  | Consolidating supervisors for closely monitored college to submit to EBA the draft and final risk assessment and joint decision documents for capital |  | As per agreed timeline (final joint decision document no later than 12 months after previous joint decision) | To monitor timely submission of draft and final risk assessment and joint decision documents | Ongoing
Joint Decision on liquidity:
|  | Consolidating supervisors for closely monitored colleges to submit to EBA the timeline for reaching joint decision on liquidity adequacy (as set out in the ITS) prepared and agreed by the college. It is to be noted that this is a new requirement for colleges and joint liquidity decision needs to be reached by 31 December 2014 at latest. |  | By 28 February 2014 | To monitor roll out of agreed timeline for reaching joint liquidity decision | Ongoing
|  | Consolidating supervisors for closely monitored colleges to submit to EBA the draft and final risk assessment and joint decision documents for liquidity |  | As per agreed timeline (final joint decision document no later than 31 December 2014) | To monitor timely submission of draft and final risk assessment and joint decision documents | Ongoing
| Emergency plans | Consolidating supervisors for closely monitored colleges to submit to EBA updated college emergency plan as agreed by the college |  | Ongoing | To collect and maintain a database with all college emergency plans | Ongoing
Regular college activities | Recovery plans | Consolidating supervisors for closely monitored colleges to submit to EBA a clear timeline for college discussions on recovery plans |  | By 28 March | To follow up on compliance with EBA recommendation on development and assessment of recovery plans | Ongoing
AQR | Asset quality review coordinated by consolidating supervisors | Consolidating supervisors for closely monitored colleges to communicate to EBA an agreement on performance of AQR and timeline as agreed by the college |  | By 31 January | To follow up on compliance with EBA recommendation on AQR | Ongoing
Capital preservation | Recommendation on the preservation of Core Tier 1 capital | Consolidating supervisors for closely monitored colleges to discuss capital plans and possible waivers with the supervisory college and communicate to EBA a timeline for further college discussions on this subject if any more are planned in 2014. |  | By 28 February 2014 | To follow up on compliance with EBA recommendation on capital preservation | Ongoing
Secure information exchange | Secure information exchange between competent authorities | Competent authorities willing to use the EBA IT collaboration tool to express their interest to EBA |  | Ongoing | To promote the use of the EBA IT Collaboration tool | Ongoing
[5 empty] | To provide training on the use of the tool to the competent authorities interested in adopting the tool | Ongoing
[5 empty] | To improve the technical support relevant for the use of the tool | Ongoing
Other colleges | Communication with other colleges | Consolidating supervisors to notify EBA of any changes in contact details |  | Ongoing | To maintain a contact list for the other colleges | Ongoing
[5 empty] | To establish regular updates on EBA policy work and home-host related issues for the other colleges on a 'group-basis' | By 28 March