## accomplished timeline 2009
| CEBS Work Programme 2009 (accomplished timeline) |  | Priority | January | February | March | April | May | June | July | August | September | October | November | December
| CEBS Meetings |  |  | March: 3-4; June: 18; October: 7; December: 2-3
Crisis management
1 | Crisis management - colleges | Recommendations for colleges in crisis situations, including procedures and operational list of information items (factbook), update of the range of practises paper | 1 | bar: January to September
[14 empty] | incorporated in the college draft guidelines | * (see item 8)
2 | Crisis management - Facilitating role of CEBS | CEBS to implement practical tools to facilitate information exchange between members - follow-up of the 2008 work | 1 | January: ongoing
ongoing
3 | Crisis management - Task force on crisis events | To analyse the supervisory implications of the national “rescue plans” and to draw conclusions and recommendations for addressing crisis events in the future | 1 | bar: January to March
*
87 | Crisis management - Task force on risk management | Enhanced guidelines to strengthen bank's risk management practices | 1 | bar: January to March
*
Early intervention mechanisms
4 | Early intervention mechanisms | Survey on early intervention measures - response to COM letter | 1 | bar: January to March
*
new | Early intervention mechanisms | CEBS comment paper on COM consultation on the review of the deposit guarantee schemes directives | 1 | bar: June to July
*
5 | Early intervention mechanisms | CEBS policy input to COM consideration on Early Intervention and Bank Resolution (also linked to Intra group asset transferability and with deposit guarantee schemes) | 1 | July: ongoing
|  |  |  | * | [5 empty] | ongoing
Periodic risk assessment
6 | Regular risk assessment of EU banking sector | Development of the methodology and processes for the regular risk assessment and preparation of the reports for March and September EFC-FCT | 1
*
7 | JCFC | Annual macroprudential report on Financial Conglomerates to EFC-FST Sep 09 | 2 | bar: January to September
*
Colleges of supervisors and other network mechanisms
8 | Supervisory colleges | CEBS good practices paper on the functioning of colleges | 1 | bar: January to March
*
57b | Home-Host cooperation/ Supervisory colleges | CEBS Liquidity Identity Card | 1 | bar: January to June
*
new | Home-Host cooperation | CEBS Advice on the information to be exchanged under Article 42 CRD | 1 | bar: February to May
*
88 | Supervisory colleges | Colleges established for all major cross-border banks in Europe by the end of 2009 | 1
*
9 | Databases on certain topics | Updated databases on 1) third country equivalence, 2) MoU's and 3) Russian presence | 3 | January: ongoing
ongoing
10 | Enforcement | Adequate exchange of information | 3 | January: ongoing
ongoing
Supervisory reporting
11 | Streamlining FINREP | Proposal for a streamlined FINREP framework | 1
[6 empty] | * | [8 empty] | *
12 | Revised guidelines on COREP | Revised COREP framework due to CRD II amendments | 1 | January: ongoing
ongoing
13 | Reporting Implementation questions | Answer IQs and maintain process | 2 | January: ongoing
ongoing
14 | Reporting - XBRL | Proposal for a revised FINREP XBRL taxonomy | 2
*
15 | Reporting - JEGR | Proposal on aligning statistical and supervisory reporting | 2 | bar: January to September
*
Training programs
16 | 3L3 cross sectoral trainings / seminars and workshops | Training programs delivered | 1 | January: ongoing
ongoing
new | 3L3 Manual on Training process | 3L3 Manual on Training process (linked to EU funding) | 1
*
17 | Supervisory culture convergence | Sectoral training programs and staff exchanges delivered | 1 | January: ongoing
ongoing
18 | JCFC | Training program for supervisors of Financial Conglomerates | 2 | January: ongoing
ongoing
Peer review exercises
19 | Peer Review exercise | Peer review exercise 2009 on colleges to be executed in conformity with the revised peer review protocol | 2
finalisation in 2010
Supervisory disclosures
20 | Supervisory Disclosure | Extension of the framework (tables and guidance) | 2
finalisation January 2010
Mediation
21 | Mediation | Case study | 2 | bar: January to June
on hold in view of institutional developments
Amendments to the CRD
22 | Own Funds - hybrids guidelines | Supervisory guidelines on hybrids (follow up on advice) | 1 | bar: January to September
*
new | Own Funds - guidelines on Art 57 a) | Implementation guidelines on instruments referred to in Art. 57(a) | 1 | bar: July to December
finalisation in 2010
23 | Large Exposures | Implementation guidelines developed, based upon advice and CRD changes | 2
*
24 | National Discretions | Update of the supervisory disclosure framework on NDs | 2
finalisation January 2010
25 | National Discretions | Follow up work to CEBS advice | 2 | bar: May to June
*
26 | Incremental default risk | Guidelines developed, based on new revised CRD and guidelines from the BCBS | 2
Waiting the outcome of the CRD review - work on this area was postponed to 2010
27 | Scope of CRD - exemption according to Art. 3 of Dir 2006/48/EC | Supervisory guidelines to enhance convergence of supervisory practices in this regard | 3 | bar: October to December
postponed to 2010 - started in Q1 of 2010
89 | Securitisation activities | Advice to COM on the effectiveness of the minimum retention requirements in Art 122 a | 1 | bar: May to October
*
90 | Securitisation activities | Position paper regarding the relationship between banks and SIVs and other securitisation vehicles | 1 | bar: January to March; October to December
abandonned
new | Supplementary measures | Proposals on a supplementary measure, including back-testing exercises | 1 | bar: March to September
*
28 | Own Funds - hybrids network | Network for information exchange (eg.on hybrids) | 3 | January: ongoing
ongoing
Implementation of the CRD
29 | CRD Transposition Questions | Provide answers and maintain process | 2 | January: ongoing
ongoing
30 | Down turn LGD | Paper on range of practices | 2 | bar: January
postponed
31 | Custodian banks | Investigate and if applicable address inconsistencies in the treatment of custodians / avoid double regulation | 2 | bar: January to June
*
32 | Credit Rating Agencies | Follow up work on COM's proposal for a Regulation on CRAs | 2 | January: ongoing
ongoing
33 | Validation | Update of GL 10 (validation) | 3
postponed in view of developments in the CRA regulation
34 | Passporting | Agreement between authorities regarding information to be shared | 3 | bar: January to June
*
35 | Operational Risk | Q&A's on AMA implementation issues and a implementation paper (range of practises papers) | 3
abandonned
86 | CCPs | Monitoring of the EU work | 2 | January: on going
on going
Pro-cyclicality
36 | Capital & Procyclicality | CEBS report with operational proposals regarding recessionary scenarios (credit risk in banking book) to EFC | 2 | bar: January to March
*
37 | Procyclicality and accounting | Analysis of procyclicality in accounting impairment and provisioning | 2 | bar: January to September
*
38a | TFICF - procyclicality | Biannual reports to EU COM | 2 | bar: January to October
*
38b | TFICF - capital monitoring | Semi annual reports to CEBS and BSC | 2
[6 empty] | 1st report to CEBS | [6 empty] | 2nd report to CEBS
Operational risk
39 | Operational Risk | Lessons learned Soc Gen case integrated in regulatory OpRisk framework | 2 | bar: January to June
finalisation in 2010
new | Operational Risk | Guidelines on Operational Risk Mitigation techniques | 2
*
new | Operational Risk | Compendium, Guidelines on operational risk issues (allocation, use test, scope) | 2 | bar: January to September
*
Pillar 2
40 | Pillar 2 - RAS and SREP | Guidelines on the joint assessment process | 1 | bar: March to December
finalisation in 2010
41 | Pillar 2 - RAS and SREP | Implementation study of RAS in Member States | 2 | bar: October to December
42 | Pillar 2 - stress testing | Range of practises paper on the supervisory approaches to stress testing under Pillar 2 | 1 | bar: July to December
*
43 | Pillar 2 - stress testing | Revised guidelines on stress testing | 2 | bar: July to December
finalisation in 2010
44 | Pillar 2 - Internal governance | Report on the implementation of the guidelines on internal governance (range of practices) | 3 | bar: July to December
finalisation in 2010
45 | Pillar 2 -concentration risk | Update of the general (introductory part) of the guidelines and developing a section on inter-risk concentrations | 1
*
46 | Pillar 2 -concentration risk | Update of the section of the guidelines on credit concentration risk | 1
*
47 | Pillar 2 -concentration risk | Developing sections on other risk concentrations (incl market, operational risk, liquidity/funding risk, business risk) | 2 | bar: July to December
*
48 | Pillar 2 - business/strategic risk | Range of practices paper, possibly followed by guidelines on business/strategic risk | 3 | bar: January to September
postponed to 2010
49 | Pillar 2 - reputational risk | Range of practices paper, possibly followed by guidelines on reputational risk | 3 | bar: October to December
postponed to 2010
50 | ECM (Pillar 2) | Assistance in finalisation of the CEBS global report on results and main finding of the ECM Project | 3 | bar: January to June
abandonned
51 | ECM follow-up (Pillar 2) | Developing high-level criteria for assessing ECMs used in ICAAP in the context of the SREP | 3 | bar: April to December
abandoned
52 | ECM follow-up (Pillar 2) | Range of practices paper on assessing risk sensitive capital allocation arrangements within groups | 3 | bar: April to December
abandoned
53 | ECM follow-up (Pillar 2) | Any other follow-up work as identified in the global report | 3 | bar: July to December
abandoned
54 | Pillar 2 - Diversification | Possible follow-up after the public consultation process and, if necessary, after completion of the ECM examination project | 3 | January: deadline to be advised
abandonned
55 | Pillar 2 - Interest rate risk in the banking book | Range of practises paper on the treatment of interest rate risk in the banking book in Pillar 2 | 3 | bar: July to December
postponed to 2010
56 | Pillar 2 - Interest rate risk in the banking book | Possible update of the existing guidelines (depending on the outcome of the range of practices) | 3 | bar: July to December
postponed to 2010
Remuneration risk
new | Remuneration risk | High- level Principles for Remuneration Policies | 1 | bar: January to April
*
new | Remuneration risk | Implementation study | 1 | bar: September to December
*
Liquidity risk management and supervision
57a | Liquidity risk management and supervision | Follow-up work on CEBS's 30 recommendations - detailed guidance on liquidity buffers | 1
*
Transparency and disclosure
58a | Banks' Transparency on market turmoil related activities | Report on the transparency of banks (with possible policy recommendations at later stage) | 1
[9 empty] | * |  |  |  | *
58b | Banks' Transparency on securitization activities | Assess and report on the proposals on securitization made by the industry: assessment of the templates developed by the EBF and supervisory relevance of the information provided | 1 | bar: January to March
*
59 | Pillar 3 Implementation | Update of the Pillar 3 implementation study of 2007 (including setup of structure allowing ongoing update) | 3 | bar: January to June
*
Monitoring of accounting and auditing standards developments
60 | Valuation of illiquid and complex financial instruments | Follow-up of developments regarding issues identified in 2008 report | 1 | bar: January to June
*
61 | Monitoring developments in accounting standards | Comment letters / input to the IASB / EFRAG | 2 | January: ongoing
ongoing
62 | Monitoring developments in auditing standards | Comment letters / input to the IAASB | 2 | January: ongoing
ongoing
63 | Prudential filters follow up work | Update on the guidelines on prudential filters (link to work on own funds by the EGPR) | 2 | bar: January to June
*
Financial conglomerates
64 | JCFC | Oral report to the EFCC on 1st part of the CfA on the FCD review | 2 | bar: January to February
*
65 | JCFC | Consultation paper on differences in MS implementation of the FCD to be issued by end Q1 2009 and finalised by end 09 (tbc) | 2
*
66 | JCFC | Annual notification of list of Financial Conglomerates | 2 | bar: January to July
*
67 | JCFC | Carry out micro-prudential crisis related work, in particular to examine potential contagion risks between banks/insurers in financial conglomerates | 2 | bar: January to June
*
3L3 work program
68 | 3L3 - Crisis handling | Develop a common contact list, identify lessons learned from the crisis, explore the development of principles or guidelines for remuneration policies and incentive schemes, consider changes to current supervisory structures and procedures | 1 | bar: January to March
*
69 | 3L3 - Colleges | Update of the 10 Common principles for colleges of supervisors in order to ensure greater efficiency and effectiveness of communication and exchange of information during times of crisis | 1 | bar: January to March
*
70 | 3L3 report on delegation | Will deal with any possible follow-up work to their 2008 work on delegation of decisions/responsibilities. | 2 | bar: January to March
*
71 | 3L3 - AML TF | Practical guidelines on the implementation of the 3rd EU AML Directive | 2 | bar: January to September
*
72 | 3L3 report on Internal Governance | Cross sector guidance on internal governance, and identify consequences of differences in Level 1 Text/ Level 2 measures | 3 | bar: January to March
finalisation in 2010
73 | 3L3 report on non cooperative jurisdictions | 1) Annual report on non cooperative jurisdictions 2) Database to record members updates | 3 | bar: January to September
*
74 | 3L3 Fit & Proper Requirements | 3L3 Guidelines on fit & proper requirements | 3
postponed
new | Packaged Retail Investment Products (PRIPs- previously known as substitute products) | 3L3 contribution to the Commision Communication of 29th April 2009 | 3 | bar: September to November
*
Key:
| Deliverable | *
Planned
Accomplished