## CEBS deliverables 2009
CEBS deliverables 2009
Priority: 1 = high, 2 = medium, 3 = low
|  | Area of Work | Deliverable | Deadline | Status | Priority (1,2,3) | Origin of request | Secretariat resource implication | Is there a link between the activity and a problem in an EU-wide or single market? (market inefficiency) | Is the problem due to market failure? (e.g. information asymmetry, market power or lack of competition, failure of a key player in a market) | Is the problem due to regulatory failure? | What regulatory objective is threatened by the problem? (e.g. market confidence, financial stability, proper functioning of the financial system, consumer protection, public awareness, reduction of financial crime) | Assess the likelihood that there will be a market-based solution over time without regulatory intervention? (0-4) | Which CEBS specific objective is the activity aiming for? | Do you need help in cunduction screening IA?
| Crisis management | [6 empty] | +0.5 FTE
1 |  | Crisis management - colleges | Recommendations for colleges in crisis situations, including procedures and operational list of information items (factbook), update of the range of practises paper | Q1-Q3 2009 | on going | 1 | CEBS initiative
2 |  | Crisis management - Facilitating role of CEBS | CEBS to implement practical tools to facilitate information exchange between members - follow-up of the 2008 work | Q1-Q4 2009 | on going | 1 | CEBS initiative
3 |  | Crisis management - Task force on crisis events | To analyse the supervisory implications of the national “rescue plans” and to draw conclusions and recommendations for addressing crisis events in the future | Q1 2009 | on going | 1 | CEBS initiative
87 |  | Crisis management - Task force on risk management | Enhanced guidelines to strengthen bank's risk management practices | Q1 2009 | on going | 1 | EFC Roadmap
Early intervention mechanisms
4 |  | Early intervention mechanisms | Survey on early intervention measures - response to COM letter | Q3 2008 - Q1 2009 | on going | 1 | EU COM letter
5 |  | Early intervention mechanisms | Policy input to COM White Paper/ supervisory guidelines / CEBS stance, and is linked with issues on asset transferability and with deposit guarantee schemes | Q4 2008 - Q1 2009 | future work | 1 | EU COM White Paper on early intervention
| Periodic risk assessment | [6 empty] | +0.5 FTE
6 |  | Regular risk assessment of EU banking sector | 1) Development of the methodology and processes, 2) bi-annual reporting to the EFC 3) work on establishing a 3L3 cross sector risk assessment framework | Q1-Q4 2009 | on going | 1 | ECOFIN - EU COM
7 |  | IWCFC | Annual macroprudential report on Financial Conglomerates to EFC-FST Sep 09 | Q3 2009 | on going | 2 | ECOFIN - EU COM
Colleges of supervisors and other network mechanisms
8 |  | Supervisory colleges | 1) Good practices paper on supervisory practices, 2) Operational guidelines on the functioning of colleges. | Q1 2009 | on going | 1 | CEBS initiative CRD
88 |  | Supervisory colleges | College established for all major cross-border banks in Europe by the end of 2009 | Q4 2009 | on going | 1 | EFC Roadmap
9 |  | Databases on certain topics | Updated databases on 1) third country equivalence, 2) MoU's and 3) Russian presence | Q1 2009 | on going | 3 | CEBS initiative
10 |  | Enforcement | Adequate exchange of information | Q1-Q4 2009 | on going | 3 | CEBS initiative
Supervisory reporting
11 |  | Streamlining FINREP | Proposal for a streamlined FINREP framework | Q1 2009 | on going | 1 | ECOFIN |  | Yes | No | Yes, |  |  | 4
12 |  | Streamlining COREP | Proposal for a streamlined COREP framework | Q1 2010 | on going | 1 | ECOFIN | [6 empty] | 4
13 |  | Reporting Implementation questions | Answer IQs and maintain process | Q1-Q4 2009 | on going | 2 | CEBS initiative |  | No |  |  |  |  | 2
14 |  | Reporting - XBRL | Proposal for a revised XBRL taxonomy | Q1 2009 - Finrep Q1 2010 - Corep | on going | 2 | CEBS initiative | [6 empty] | 4
15 |  | Reporting - JEGR | Proposal on aligning statistical and supervisory reporting | Q4 2009 | on going | 2 | ESCB | [6 empty] | 4
| Training programs | [6 empty] | +0.5 FTE
16 |  | 3L3 cross sectoral trainings / seminars and workshops | Training programs delivered | Q1-Q4 2009 | on going | 1 | CEBS initiative
17 |  | Supervisory culture convergence | Sectoral training programs and staff exchanges delivered | Q1-Q4 2009 | on going | 1 | CEBS initiative
18 |  | IWCFC | Training program for supervisors of Financial Conglomerates | Q1-Q4 2009 | on going | 2 | CEBS initiative
| Peer review exercises | [6 empty] | +0.25 FTE
19 |  | Peer Review exercise | Perform a peer review exercise in conformity with the peer review protocol | Q1-Q4 2009 | on going | 2 | CEBS initiative | IT system to be developed
Supervisory disclosures
20 |  | Supervisory Disclosure | Extension of the framework (tables and guidance) | Q1-Q4 2009 | on going | 2 | CEBS initiative | IT system to be developed
| Mediation | [6 empty] | +0.25 FTE
21 |  | Mediation | Case study | Q1-Q2 2009 | future work | 2 | CEBS initiative
Amendments to the CRD
22 |  | Own Funds - hybrids guidelines | Supervisory guidelines on hybrids (follow up on advice) | Q3 2009 | on going | 1 | CEBS initiative - CRD
23 |  | Large Exposures | Guidelines developed, based upon advice and CRD changes | Q2 2009 (CP) Q1 2010 (guidelines) | on going | 2 | CEBS initiative
24 |  | National Discretions | Update of the supervisory disclosure framework on NDs | Q1-Q4 2009 | on going | 2 | CEBS initiative
25 |  | National Discretions | Follow up work for comitology changes and update guidelines and SD framework | Q1-Q4 2009 | future work | 2 | CEBS initiative
26 |  | Incremental default risk | Guidelines developed, based on new revised CRD and guidelines from the BCBS | Q2 2009 | future work | 2 | CRD
27 |  | Scope of CRD - exemption according to Art. 3 of Dir 2006/48/EC | Supervisory guidelines to enhance convergence of supervisory practices in this regard | Q4 2009-Q1 2010 | future work | 3 | CRD
89 |  | Securitisation activities | Implementation guidance on the revised regulation, notably on retention clauses | Q2 2009-2010 | future work | 1 | CRD
90 |  | Securitisation activities | Position paper regarding the relationship between banks and SIVs and other securitisation vehicles | Q1 2009 | future work | 1 | CEBS initiative
28 |  | Own Funds - hybrids network | Network for information exchange (eg.on hybrids) | Q1-Q4 2009 | future work | 3 | CEBS initiative
Implementation of the CRD
29 |  | CRD Transposition Questions | Provide answers and maintain process | Q1-Q4 2009 | on going | 2 | CEBS initiative | [6 empty] | 4
30 |  | Down turn LGD | Paper on range of practices | 2009-01-01 | on going | 2 | CEBS initiative
31 |  | Custodian banks | Possible follow up work to address gaps, if identified in 2008 work | Q2 2009 | on going | 2 | Council CEBS initiative
32 |  | Credit Rating Agencies | Follow up work on COM's proposal | Q1-Q4 2009 | on going | 2 | CEBS initiative
33 |  | Validation | Update of GL 10 (validation) | Q4 2009 | future work | 3 | CEBS initiative
34 |  | Passporting | Agreement between authorities regarding information to be shared | Q1 2009 | on going | 3 | CEBS initiative
35 |  | Operational Risk | Q&A's on AMA implementation issues and a implementation paper (range of practises papers) | Q1-Q4 2009 | future work | 3 | CEBS initiative - Industry
86 |  | CCPs | Monitoring of the EU work | Q1-Q4 2009 | on going | 2 | CEBS initiative
Pro-cyclicality
36 |  | Capital & Procyclicality | Report with an operational proposal regarding recessionary scenarios (credit risk in banking book) - Report to EFC (in liaison with BSC) | Q4 2008 | on going | 2 | CEBS initiative - request by FR Presidency
37 |  | Capital & Procyclicality | Operational proposals on extended scope (e.g. credit in trading book) - Messages on provisioning issues (with EGFI input) | Q1 - Q2 2009 | future work | 2 | CEBS initiative
38 |  | TFICF - procyclicality | Quarterly reports to COM | Q1 2009-2012 | on going | 2 | EU COM |  | Possible | No | Possible | financial stability | 0 | 1
Operational risk
39 |  | Operational Risk | Lessons learned Soc Gen case integrated in regulatory OpRisk framework | Q1-Q2 2009 | future work | 2 | CEBS initiative
Pillar 2
40 |  | Pillar 2 - RAS and SREP | Guidelines on the joint assessment process | Q4 2009 | on going | 1 | CEBS initiative
41 |  | Pillar 2 - RAS and SREP | Implementation study of RAS in Member States | Q4 2008 | on going | 2 | CEBS initiative
42 |  | Pillar 2 - stress testing | Range of practises paper on the supervisory approaches to stress testing under Pillar 2 | Q2-Q3 2009 | future work | 1 | CEBS initiative
43 |  | Pillar 2 - stress testing | Possible update of the existing guidelines (depending on the outcome of the range of practices) | Q3-Q4 2009 | future work | 2 | CEBS initiative
44 |  | Pillar 2 - Internal governance | Report on the implementation of the guidelines on internal governance (range of practices), investigating possibilities/need for any further work on guidelines | Q2-Q4 2009 | future work | 3 | CEBS initiative
45 |  | Pillar 2 -concentration risk | Update of the general (introductory part) of the guidelines and developing a section on inter-risk concentrations | Q4 2008 - Q4 2009 | on going | 1 | CEBS initiative
46 |  | Pillar 2 -concentration risk | Update of the section of the guidelines on credit concentration risk | Q4 2008 - Q4 2010 | on going | 1 | CEBS initiative
47 |  | Pillar 2 -concentration risk | Developing sections on other risk concentrations (incl market, operational risk, liquidity/funding risk, business risk) | Q2-Q4 2009 | future work | 2 | CEBS initiative
48 |  | Pillar 2 - business/strategic risk | Range of practices paper, possibly followed by guidelines on business/strategic risk | Q1-Q3 2009 | future work | 3 | CEBS initiative
49 |  | Pillar 2 - reputational risk | Range of practices paper, possibly followed by guidelines on reputational risk | Q3-Q4 2009 | future work | 3 | CEBS initiative
50 |  | ECM (Pillar 2) | Assistance in finalisation of the CEBS global report on results and main finding of the ECM Project | Q1-Q2 2009 | future work | 3 | CEBS initiative
51 |  | ECM follow-up (Pillar 2) | Developing high-level criteria for assessing ECMs used in ICAAP in the context of the SREP | Q2-Q4 2009 | future work | 3 | CEBS initiative
52 |  | ECM follow-up (Pillar 2) | Range of practices paper on assessing risk sensitive capital allocation arrangements within groups | Q2-Q4 2009 | future work | 3 | CEBS initiative
53 |  | ECM follow-up (Pillar 2) | Any other follow-up work as identified in the global report | Q3-Q4 2009 | future work | 3 | CEBS initiative
54 |  | Pillar 2 - Diversification | Possible follow-up after the public consultation process and, if necessary, after completion of the ECM examination project | Deadline to be advised | future work | 3 | CEBS initiative - Industry
55 |  | Pillar 2 - Interest rate risk in the banking book | Range of practises paper on the treatment of interest rate risk in the banking book in Pillar 2 | Q3-Q4 2009 | future work | 3 | CEBS initiative
56 |  | Pillar 2 - Interest rate risk in the banking book | Possible update of the existing guidelines (depending on the outcome of the range of practices) | 2010 | future work | 3 | CEBS initiative
Liquidity risk management
57 |  | Liquidity risk management and supervision | Follow-up work on CEBS's 30 recommendations - detailed guidance on liquidity buffers, internal transfer mechanism and criteria for assessing internal methodologies as well as elaboration of a common minimum set of information requirements and survey of th | Q1-Q4 2009 | on going | 1 | CEBS initiative
Transparency and disclosure
58 |  | Banks' Transparency on market turmoil related activities | Report on the transparency of banks, with possible policy recommendations | Q3-Q4 2009 | on going | 1 | CEBS initiative
58b |  | Banks' Transparency on securitization activities | Assess and report on the proposals on securitization made by the industry: assessment of the templates developed by the EBF and supervisory relevance of the information provided | Q1 2009 | future work | 1 | G20
59 |  | Pillar 3 Implementation | Update of the Pillar 3 implementation study of 2007 (including setup of structure allowing ongoing update) | Q2-Q3 2009 | on going | 3 | CEBS initiative
Monitoring of accounting and auditing standards developments
60 |  | Valuation of illiquid and complex financial instruments | Follow-up of developments regarding issues identified in 2008 report | Q2-Q3 2009 | on going | 1 | CEBS initiative - EU COM
61 |  | Monitoring developments in accounting standards | Comment letters / input to the IASB / EFRAG | Q1-Q4 2009 | on going | 2 | CEBS initiative
62 |  | Monitoring developments in auditing standards | Comment letters / input to the IAASB | Q1-Q4 2009 | on going | 2 | CEBS initiative
63 |  | Prudential filters follow up work | Update on the guidelines on prudential filters (link to work on own funds by the EGPR) | Q1-Q2 2009 | on going | 2 | CEBS initiative
Financial conglomerates
64 |  | IWCFC | Oral report to the EFCC on 1st part of the CfA on the FCD review | 2009-01-01 | Done | 2 | EU COM
65 |  | IWCFC | Consultation paper on differences in MS implementation of the FCD to be issued by end Q12009 and finalised by end 09 (tbc) | Q1-Q4 2009 | on going | 2 | EU COM
66 |  | IWCFC | Annual notification of list of Financial Conglomerates | Q2 2009 | on going | 2 | EU COM
67 |  | IWCFC | Carry out micro-prudential crisis related work, in particular to examine potential contagion risks between banks/insurers in financial conglomerates | Q2 2009 | on going | 2 | EU COM
| 3L3 work program | [6 empty] | +0.5 FTE
68 |  | 3L3 - Crisis handling | Develop a common contact list, identify lessons learned from the crisis, explore the development of principles or guidelines for remuneration policies and incentive schemes, consider changes to current supervisory structures and procedures | Q1-Q4 2009 | on going | 1 | 3L3
69 |  | 3L3 - Colleges | Update of the 10 Common principles for colleges of supervisors in order to ensure greater efficiency and effectiveness of communication and exchange of information during times of crisis | Q1-Q4 2009 | Done | 1 | 3L3
70 |  | 3L3 report on delegation | Will deal with any possible follow-up work to their 2008 work on delegation of decisions/responsibilities. | Q1 2009 | on going | 2 | 3L3
71 |  | 3L3 - AML TF | Practical guidelines on the implementation of the 3rd EU AML Directive | Q1-Q4 2009 | on going | 2 | 3L3
72 |  | 3L3 report on Internal Governance | Cross sector guidance on internal governance, and identify consequences of differences in Level 1 Text/ Level 2 measures | Q1 2009 | on going | 3 | 3L3
73 |  | 3L3 report on non cooperative jurisdictions | 1) Annual report on non cooperative jurisdictions 2) Database to record members updates | Q3 2009 | on going | 3 | 3L3
74 |  | 3L3 Fit & Proper Requirements | 1) Guidelines on fit & proper requirements and 2) explore the feasibility of a common database on F&P outcomes | Q1-Q4 2009 | on going | 3 | 3L3
75 |  | Substitute products | Work to be reassessed following the delivery of the Commission's work | Deadline to be advised | future work | 3 | 3L3
| CEBS processes | [6 empty] | +0.5 FTE
76 |  | CEBS processes - work program | Annual work program set up and quarterly report prepared on progress | Q1-Q4 2009 | on going | 1 | EU COM - CEBS initiative
77 |  | CEBS processes - annual report | Annual report prepared | Q2 2009 | on going | 1 | EU COM - CEBS initiative
78 |  | CEBS processes - external communication | Press questions answered as first point of contact, speeches coordinated and website managed | Q1-Q4 2009 | on going | 1 | CEBS initiative | IT system to be developed
79 |  | CEBS processes - Briefings EU institutions | Briefings for SG and chair CEBS co-ordinated on EU institutions | Q1-Q4 2009 | on going | 1 | CEBS initiative
80 |  | CEBS processes - QMV | QMV applied in transparent way by CEBS Committee | Q2 2009 | future work | 1 | EU COM - CEBS initiative
81 |  | CEBS processes - internal communication | Due process and internal communication enhanced by means of internal newsletters and enhanced use of the members only website | Q4 2009 | on going | 2 | CEBS initiative
82 |  | CEBS processes - procedures | Internal processes of CEBS secretariat made explicit and transparant by the development of internal guidance book | Q4 2009 | future work | 2 | CEBS initiative
83 |  | CEBS processes - communication strategy | Communication strategy developed | Q1 2009 | on going | 2 | CEBS initiative
84 |  | Queries | Develop common query system | Q4 2008 - Q1 2009 | future work | 2 | CEBS initiative | IT system to be developed | No | Yes, IT development recources, IT maintenance ressources | 2