## Roadmap
N.B. For planning purposes only, all dates and content subject to change - Information as known to EBA IT as of | [6 empty] | 2015-09-01
Information from EBA oversight or regulation should be assumed to take precedence
Dictionary / DPM Version | Public Draft Taxonomy Release Date planned (finalised) | Content | [5 empty] | Expected Reporting Dates |  |  | Specific Reporting Versions
[8 empty] | Expected notional file content date | Expected Last Reporting Date -> NCA | Expected Final remittance date -> EBA | Monthly |  |  | Quarterly |  |  | Annually
|  | COREP | FINREP | Asset Encumbrance | Fundings plans | Benchmarking |  |  |  |  | COREP |  |  | COREP OF, LE, LR, NSFR | FINREP Financial Reporting | AE Asset Encumbrance | FP Funding Plans | SBP Benchmarking
[11 empty] | LCR | LCR_DA | ALM |  |  |  |  | IMV | Main
2.0 | 09/2013 (02/12/2013) | COREP 2.0.1 | FINREP 2.0.1 |  |  |  |  | 2014-12-31 | 2015-01-31 | 2015-02-20 | 2.0.3
|  |  | Unused | [5 empty] | 2015-02-11 | 2015-02-25 |  |  |  | 2.0.3 | 2.1.1 | 1.0.1
2.1 | 03/2014 (08/07/2014) | COREP 2.0.2 | FINREP 2.1.0 | AE 1.0.0 |  |  |  |  | 2015-09-30 | 2015-11-15 | [6 empty] | 1.0.2
|  | Amendments | Amendments FBE/NPE | Unused |  |  |  | 2015-01-31 | 2015-02-15 | 2015-03-01 | 2.0.3
[8 empty] | 2015-02-28 | 2015-03-15 | 2015-03-30 | 2.0.3
2.2 | 08/2014 (18/08/2014) | COREP 2.0.3 | FINREP 2.1.1 | AE 1.0.1 | FP 1.0.0 |  |  | 2015-03-31 | 2015-04-15 | 2015-04-29 | 2.0.3
|  | Amendments | Amendments | Amendments | Unused |  |  |  | 2014-05-12 | 2014-05-28 |  |  |  | 2.0.3 | 2.1.1 | 1.0.1
[8 empty] | 2015-04-30 | 2015-05-15 | 2015-06-01 | 2.0.3
[8 empty] | 2015-05-31 | 2015-06-15 | 2015-06-29 | 2.0.3
2.3 (2015-A) | Q4/2014 (02/03/2015) | COREP 2.1.0 | FINREP 2.1.2 |  | FP 1.0.1 | SBP 1.0.0 |  | 2015-06-30 | 2015-07-15 | 2015-07-29 | 2.1.0
|  | ALM Amendments | Amendments |  | Amendments Unused | New Reporting Unused |  |  | 2015-08-11 | 2015-08-25 |  |  |  | 2.1.0 | 2.1.2 | 1.0.1
[9 empty] | 2015-09-30 | 2015-11-15 | [6 empty] | 1.0.2
[8 empty] | 2015-07-31 | 2015-08-17 | 2015-08-31 | 2.1.0
2.3.1 (2015-A-1) | (08/05/2015) |  |  |  | FP 1.0.2 | SBP 1.0.1 |  | 2015-08-31 | 2015-09-15 | 2015-09-29 | 2.1.0
2.3.2 (2015-A-2) | 07/2015 |  | 2.1.3 (+Ind) |  |  |  |  | 2015-09-30 | 2015-10-15 | 2015-10-29 | 2.1.0
[9 empty] | 2015-11-11 | 2015-11-25 |  |  |  | 2.1.0 | 2.1.2 | 1.0.1
2.4 (2015-B) | Q3/2015 | LR, LCR Changes | [5 empty] | 2015-10-31 | 2015-11-02 | 25/11/2015 (TBC) | [7 empty] | 1.0.1
|  | QA 1042 - Multicurrency |  | QA 1042 - Multicurrency |  | True multicurrency |  | N.B. LCR Regulation notionally applies from here - but reporting changes not until OJEU publication of ITS + 6 months (~05/2016)
[8 empty] | 2015-10-31 | 2015-11-16 | 2015-11-30 | 2.1.0
2.5 (2016-A) | Q1/2016 | Amendments / Corrections / Technical Evolution | [5 empty] | 2015-11-30 | 2015-12-15 | 2016-01-04 | 2.1.0
[8 empty] | 2015-12-31 | 2016-01-15 | 2016-02-01 | 2.1.0
[9 empty] | 2016-02-11 | 2016-02-25 |  |  |  | 2.1.0 | 2.1.2 | 1.0.1
2.6 (2016-B) | Q4/2016 | Trading Book Review, LE Review, SME, Mortgage Exposure, Prudent Valuation (LCR Corrigendum?) | IFRS 9 | [5 empty] | 2016-03-31 | 2016-04-30 | [6 empty] | 1.0.2
[9 empty] | 2016-04-11 | 25/04/2016 (TBC) | [8 empty] | 1.0.1
[8 empty] | 2016-01-31 | 2016-02-15 | 2016-02-25 | 2.1.0 |  | 2.1.0
[8 empty] | 2016-02-29 | 2016-03-15 | 2016-03-25 | 2.1.0 |  | 2.1.0
|  | EBA Modelling Review | [5 empty] | 2016-03-31 | 2016-04-15 | 2016-04-25 | 2.1.0 |  | 2.1.0
[9 empty] | 2016-05-12 | 2016-05-23 |  |  |  | 2.1.0 | 2.1.2 | 1.0.1
Italics = to be confirmed / longer term | [7 empty] | 2015-04-30 | 2015-05-15 | 2015-05-25 | 2.1.0 |  | 2.1.0
First reference date uncertain - commencement is "6 months after publication of ITS in OJEU"
FBE: Forbearance | [7 empty] | 2015-05-31 | 2015-06-15 | 2015-06-25 | 2.2.0 |  | 2.2.0
NPE : Non Performing Exposures | [8 empty] | 2015-06-30 | 2015-07-10 |  | 2.2.0
IMV: Initial market valuation (part of BM) | [7 empty] | Future Working Assumptions
SBP: Benchmarking portfolio asssessment (Internal models) | [7 empty] | Q4 2016 | [8 empty] | 1.0.2 | 1.0.2 | 1.0.2
ALM : Additional liquidity Monitoring Metrics | [7 empty] | Q2 2017
[8 empty] | Q1 2018 | [6 empty] | IFRS9
Formulas:
Expected Last Reporting Date -> NCA = WORKDAY([Expected Reporting Dates]+14,1)
Expected Last Reporting Date -> NCA = WORKDAY([Expected Reporting Dates, row above]+29,1)
Expected Final remittance date -> EBA = [Expected Reporting Dates]+30
Expected Final remittance date -> EBA = WORKDAY([Expected Reporting Dates]+29,1)
Note on I3: ojones: In general dates determined by legal texts are uncertain until final adoption of said texts and publication in e.g. Official Journal of European Union
Note on I4: ojones: Fill colour indicates DPM version to be used for this report. "File content" date is the date to be used for the content of XBRL instant elements for all facts, and in file name when submitting to ESP system. This is usually the same concept referred to as the "reference date".
Note on F20: ojones: Entry Point split to IND and CON variants
Note on G20: ojones: Entry Point split to IND and CON variants
Note on D21: ojones: Added "Individual" consolidation (i.e. Solo) report, mutually compatible with DPM 2.3(.1 )/ FINREP 2.1.2 in all other respects/for all other reports.